## Stage_report
Primary | Assigned To | % Complete | Health | Progress | End Date | Status | Active Phase | Start Date | Wave | Code | short name | tier | Program
Initiative 1: Implement a Rapid Response system | Ibaa Hanbali | 0% | Gray | Empty | 2026-12-23 17:00 | Not Started | Not Started | 2026-07-16 08:00 | Wave 2 | I001 | Rapid Response System | Tier 3 - Low Governance | 1- Healthcare & Wellness Services
Initiative 02: Stroke Management Solution Implementation | samaher abu samrah | 21% | Green | Empty | 2025-08-10 17:00 | In Progress | Planning | 2025-02-10 08:00 | Wave 2 | I002 | Stroke Management | Tier 3 - Low Governance | 1- Healthcare & Wellness Services
Initiative 3: Upgrade the Tele Health services (Tele consultation) | Amir Aziz | 90% | Green | Three Quarter | 2025-06-15 17:00 | In Progress | Closure | 2024-01-01 08:00 | Wave 1 | I003 | Telehealth – Consultation | Tier 3 - Low Governance | 1- Healthcare & Wellness Services
Initiative 4: Upgrade the Tele Health services (Tele CCU) | Amir Aziz | 51% | Green | Half | 2025-09-16 17:00 | In Progress | Procurement | 2024-10-01 08:00 | Wave 1 | I004 | Telehealth – Critical Care (TCCU) | Tier 1 - High Governance | 1- Healthcare & Wellness Services
Initiative 5:Upgrade the Tele Health services (Tele Radiology) | Amir Aziz | 58% | Green | Half | 2025-07-06 17:00 | In Progress | Implementation | 2025-01-01 08:00 | Wave 1 | I005 | Telehealth – Radiology | Tier 2 - Medium Governance | 1- Healthcare & Wellness Services
Initiative 6: Smart Operating room OR, ICU, CCU | Amir Aziz | 43% | Green | Quarter | 2025-10-14 17:00 | In Progress | Planning | 2025-01-01 08:00 | Wave 1 | I006 | Smart OR, ICU, CCU | Tier 1 - High Governance | 1- Healthcare & Wellness Services
Initiative 7: Upgrade Home care Services (OVERALL PLAN) | Khawlah Alotaibi | 44% | Green | Quarter | 2025-06-12 17:00 | In Progress | Assesment | 2024-12-01 08:00 | Wave 1 | I007 | Home Care Upgrade | Tier 2 - Medium Governance | 1- Healthcare & Wellness Services
Initiative 8: Upgrade the Remote patient monitoring | Khawlah Alotaibi | 11% | Green | Empty | 2025-12-08 17:00 | Not Started | Planning | 2025-04-01 08:00 | Wave 1 | I008 | Remote Patient Monitoring | Tier 1 - High Governance | 1- Healthcare & Wellness Services
Initiative 9: Upgrade the physician and nurses' mobile application | Ahmed Al Rayes | 0% | Green | Empty | 2026-04-21 17:00 | In Progress | Assesment | 2025-03-09 08:00 | Wave 1 | I009 | Mobile EMR Access | Tier 3 - Low Governance | 1- Healthcare & Wellness Services
Initiative 10: Upgrade EMR (Overall Plan) | Ahmed Al Rayes | 80% | Green | Three Quarter | 2025-09-14 17:00 | In Progress | Closure | 2024-09-03 08:00 | Wave 1 | I010 | EMR Upgrade | Tier 1 - High Governance | 1- Healthcare & Wellness Services
Initiative 11: OR booking system (Part of the EMR) | Ahmed Al Rayes | 1% | Green | Empty | 2026-03-03 17:00 | In Progress | Assesment | 2025-03-10 08:00 | Wave 1 | I011 | OR Booking System | Tier 1 - High Governance | 1- Healthcare & Wellness Services
Initiative 12: Upgrade Clinical decision support system (CDSS) | Amir Aziz | 23% | Green | Empty | 2026-01-05 17:00 | In Progress | Implementation | 2024-11-03 08:00 | Wave 2 | I012 | Clinical Decision Support (CDSS) | Tier 1 - High Governance | 1- Healthcare & Wellness Services
Initiative 13: Enable mobile applications for desktop solutions for ease of access for Clinical/Non-Clinical /Para Medical staff on the go | mahmoud alfaqih | 0% | Gray | Empty | 2026-12-08 17:00 | Not Started | Not Started | 2025-06-01 08:00 | Wave 2 | I013 | Mobile Access for Staff | Tier 3 - Low Governance | 1- Healthcare & Wellness Services
Initiative 14: Upgrade the Wireless Nurse Call System | samaher abu samrah | 0% | Gray | Empty | 2026-05-03 17:00 | Not Started | Not Started | 2025-12-01 08:00 | Wave 3 | I014 | Wireless Nurse Call System | Tier 3 - Low Governance | 1- Healthcare & Wellness Services
Initiative 15: Upgrading of Hugs and Kisses Infant Protection | Khawlah Alotaibi | 28% | Red | Quarter | 2024-10-01 17:00 | In Progress | Implementation | 2024-03-20 08:00 | Wave 1 | I015 | Infant Protection & Health Monitoring | Tier 2 - Medium Governance | 1- Healthcare & Wellness Services
Initiative 16: Implementation of Hand Hygiene Compliance Monitoring System (EchoLab) | samaher abu samrah | 0% | Gray | Empty | 2026-12-30 17:00 | Not Started | Not Started | 2026-06-01 08:00 | Wave 3 | I016 | Hand Hygiene Monitoring | Tier 3 - Low Governance | 1- Healthcare & Wellness Services
Initiative 17: Implement a Centralized patient monitoring system (IP Wards) | samaher abu samrah | 0% | Gray | Empty | 2026-06-03 17:00 | Not Started | Not Started | 2025-12-01 08:00 | Wave 3 | I017 | Centralized Patient Monitoring | Tier 3 - Low Governance | 1- Healthcare & Wellness Services
Initiative 18: Upgrade the Blood bank system | Amir Aziz | 24% | Green | Empty | 2025-10-05 17:00 | In Progress | Planning | 2025-01-01 08:00 | Wave 1 | I018 | Blood Bank Inventory System | Tier 2 - Medium Governance | 1- Healthcare & Wellness Services
Initiative 19: Implementing a Closed Loop Medication Administration | Amir Aziz | 72% | Green | Half | 2025-06-30 17:00 | In Progress | Implementation | 2025-01-01 08:00 | Wave 1 | I019 | Closed Loop Medication System | Tier 1 - High Governance | 1- Healthcare & Wellness Services
Initiative 20: Implement Automated Medication dispensing Machines | Amir Aziz | 39% | Green | Quarter | 2025-07-07 17:00 | In Progress | Implementation | 2025-01-01 08:00 | Wave 1 | I020 | Automated Medication Dispensing | Tier 2 - Medium Governance | 1- Healthcare & Wellness Services
Initiative 21: Implement a Pharmacy Robot | Amir Aziz | 21% | Green | Empty | 2025-09-25 17:00 | In Progress | Implementation | 2025-01-01 08:00 | Wave 1 | I021 | Pharmacy Robot | Tier 1 - High Governance | 1- Healthcare & Wellness Services
Initiative 22: Enable Integration and Interoperability fabric: Between EMR Drs Module and Insurance portals (Medication) | mahmoud alfaqih | 100% | Green | Full | 2025-08-10 17:00 | Complete | Completed | 2025-02-10 08:00 | Wave 2 | I022 | EMR Insurance Integration | Tier 3 - Low Governance | 2- Integration and Interoperability
Initiative 23: Enable Integration and Interoperability fabric: MoH (HIE/NPHIES) platform with HIS | Ibaa Hanbali | 65% | Green | Half | 2025-08-14 17:00 | In Progress | Implementation | 2025-01-01 08:00 | Wave 2 | I023 | EMR MoH Integration | Tier 3 - Low Governance | 2- Integration and Interoperability
Initiative 24: Implement and integrate the Smart medical devices | Ahmed Al Rayes | 0% | Green | Empty | 2026-09-24 17:00 | In Progress | Assesment | 2025-01-01 08:00 | Wave 1 | I024 | Smart Device EMR Integration | Tier 2 - Medium Governance | 2- Integration and Interoperability
Initiative 25: Upgrade Bedside monitoring device integration | Ahmed Al Rayes | 63% | Red | Half | 2025-04-20 17:00 | In Progress | Implementation | 2025-03-02 08:00 | Wave 1 | I025 | Bedside Monitoring Upgrade | Tier 1 - High Governance | 2- Integration and Interoperability
Initiative 26: Updating the Dallah Internal portal | Samaher Abu-samrah | 0% | Gray | Empty | 2027-07-13 17:00 | Not Started | Not Started | 2026-01-04 08:00 | Wave 3 | I026 | Internal Portal Upgrade | Tier 3 - Low Governance | 3- Digital Transformation
Initiative 27: Implement digital enablement tools | Khawlah Alotaibi | 72% | Red | Half | 2025-01-07 17:00 | In Progress | Implementation | 2024-09-03 08:00 | Wave 1 | I027 | Elearning & Training (LMS) | Tier 3 - Low Governance | 3- Digital Transformation
Initiative 28: Enhancing the Knowledge Management Tool | samaher abu samrah | 0% | Gray | Empty | 2026-01-21 17:00 | Not Started | Not Started | 2025-05-01 08:00 | Wave 2 | I028 | Knowledge Management Upgrade | Tier 3 - Low Governance | 3- Digital Transformation
Initiative 29: Digitize supply chain processes | Ehab almalahmeh | 12% | Gray | Empty | 2026-08-26 17:00 | Not Started | Implementation | 2025-05-30 08:00 | Wave 2 | I029 | Digital Supply Chain | Tier 1 - High Governance - part of ERP | 4- Business Process Automation
Initiative 30: Digitize HR solution | Ehab almalahmeh | 35% | Gray | Quarter | 2026-08-26 17:00 | Complete | Implementation | 2025-05-30 08:00 | Wave 2 | I030 | Digital HR Solutions | Tier 1 - High Governance - part of ERP | 4- Business Process Automation
Initiative 31: Digitize ﬁnance processes | Ehab almalahmeh | 0% | Gray | Empty | 2026-08-26 17:00 | Not Started | Not Started | 2025-05-30 08:00 | Wave 2 | I031 | Digital Finance Processes | Tier 1 - High Governance - part of ERP | 4- Business Process Automation
Initiative 32: Re-designing and automating various business processes through Business process management (BPM) solution | Ehab almalahmeh | 0% | Gray | Empty | 2026-11-12 17:00 | Complete | Not Started | 2026-02-22 08:00 | Wave 2 | I032 | Business Process Automation | Tier 3 - Low Governance | 4- Business Process Automation
Initiative 33: Implement an Intelligent and sustainable buildings solution | Samaher Abu-samrah | 0% | Gray | Empty | 2025-11-27 17:00 | Not Started | Not Started | 2025-05-30 08:00 | Wave 3 | I033 | Smart & Sustainable Buildings | Tier 3 - Low Governance | 5- Digital Foundation
Initiative 34: Implement an asset tracking system | Ibaa Hanbali | 0% | Gray | Empty | 2026-04-01 17:00 | In Progress | Assesment | 2025-05-30 08:00 | Wave 2 | I034 | Asset Tracking System | Tier 3 - Low Governance | 5- Digital Foundation
Initiative 35: Focus on digitization of Patient and other medical operations (eg- consent forms, prescriptions) | Ahmed Al Rayes | 46% | Green | Quarter | 2025-06-23 17:00 | In Progress | Implementation | 2024-12-01 08:00 | Wave 1 | I035 | Patient Operations Digitization | Tier 3 - Low Governance | 5- Digital Foundation
Initiative 36: Business Continuity Plan: Define and design a DR/DC plan for Dallah Health | Ibaa Hanbali | 0% | Gray | Empty | 2026-06-15 17:00 | Not Started | Not Started | 2026-02-22 08:00 | Wave 1 | I036 | Business Continuity & DR Plan | Tier 2 - Medium Governance | 5- Digital Foundation
Initiative 37: Define the cloud strategy and the cloud journey | mahmoud alfaqih | 0% | Gray | Empty | 2025-11-16 17:00 | Not Started | Not Started | 2025-08-03 08:00 | Wave 2 | I037 | Cloud Strategy & Roadmap | Tier 3 - Low Governance | 5- Digital Foundation
Initiative 38: Upgrade the ERP solution | Ehab almalahmeh | 29% | Green | Quarter | 2025-12-31 17:00 | In Progress | Implementation | 2024-12-01 08:00 | Wave 1 | I038 | ERP Upgrade | Tier 1 - High Governance | 5- Digital Foundation
Initiative 39: Implement Patient self services tools | Khawlah Alotaibi | 58% | Green | Half | 2025-06-24 17:00 | In Progress | Implementation | 2024-11-01 08:00 | Wave 1 | I039 | Patient Self Service Tools | Tier 2 - Medium Governance | 6- Patient Engagement
Initiative 40: Digital Front Door - Upgrade existing Dallah mobile application - e-pharmacy | Khawlah Alotaibi | 29% | Green | Quarter | 2025-08-17 17:00 | In Progress | Implementation | 2025-01-01 08:00 | Wave 1 | I040 | Digital Front Door – ePharmacy | Tier 2 - Medium Governance | 6- Patient Engagement
Initiative 41: Digital Front Door- Upgrade existing Dallah mobile application hospital navigation system | Khawlah Alotaibi | 28% | Gray | Quarter | 2025-12-01 17:00 | Complete | Implementation | 2025-07-01 08:00 | Wave 1 | I041 | Digital Front Door – Navigation | Tier 2 - Medium Governance | 6- Patient Engagement
Initiative 42: Digital Front Door - Upgrade existing Dallah mobile application (Admission request, & Pre-admission workflow automation) | Ahmed Al Rayes | 100% | Green | Full | 2025-02-13 17:00 | Complete | Completed | 2025-01-01 08:00 | Wave 1 | I042 | Digital Front Door – Admission Workflow | Tier 2 - Medium Governance | 6- Patient Engagement
Initiative 43: Implement digital patient identification solutions (Eg: RFID, Barocde, Wristbands) | Ahmed Al Rayes | 27% | Green | Quarter | 2025-08-28 17:00 | In Progress | Implementation | 2023-06-14 08:00 | Wave 1 | I043 | Digital Patient ID Solutions | Tier 2 - Medium Governance | 6- Patient Engagement
Initiative 44: Improve the Patient Feedback Monitoring System | Khawlah Alotaibi | 0% | Gray | Empty | 2026-03-29 17:00 | Complete | Planning | 2025-10-01 08:00 | Wave 1 | I044 | Patient Feedback System | Tier 3 - Low Governance | 6- Patient Engagement
Initiative 45: Introduce a Digital Discharge solution | Ahmed Al Rayes | 100% | Green | Full | 2025-04-15 17:00 | Complete | Completed | 2024-06-01 08:00 | Wave 1 | I045 | Digital Discharge Process | Tier 3 - Low Governance | 6- Patient Engagement
Initiative 46: Implement Queue Management Solution | Khawlah Alotaibi | 35% | Green | Quarter | 2025-09-17 17:00 | In Progress | Implementation | 2024-11-01 08:00 | Wave 1 | I046 | Queue Management System | Tier 2 - Medium Governance | 6- Patient Engagement
Initiative 47: Introduce the Bed side Information system | Ahmed Al Rayes | 15% | Green | Empty | 2025-10-02 17:00 | In Progress | Procurement | 2025-01-01 08:00 | Wave 1 | I047 | Bedside Info System | Tier 2 - Medium Governance | 6- Patient Engagement
Initiative 48:Implement & upgrade the patient engagement channels | mahmoud alfaqih | 0% | Gray | Empty | 2027-04-08 17:00 | In Progress | Assesment | 2025-09-30 08:00 | Wave 2 | I048 | Patient Engagement Upgrade | Tier 3 - Low Governance | 6- Patient Engagement
Initiative 49: Implement a CRM solution to streamline the overall patient experience journey (Marketing Sales Social, Patient 360 Persona, Sales Accelerator, Customer Service Insights, Power BI & Analytics) | samaher abu samrah | 0% | Green | Empty | 2026-10-01 17:00 | Not Started | Assesment | 2025-03-25 08:00 | Wave 2 | I049 | CRM for Patient Experience | Tier 3 - Low Governance | 6- Patient Engagement
Initiative 50: Implement a patient portal that is integrated with the EMR | samaher abu samrah | 100% | Green | Full | 2025-03-17 17:00 | Complete | Completed | 2024-01-01 08:00 | Wave 1 | I050 | Integrated Patient Portal | Tier 3 - Low Governance | 6- Patient Engagement
Initiative 51: Upgrade The Patient Education System | Amir Aziz | 31% | Green | Quarter | 2025-10-01 17:00 | In Progress | Procurement | 2025-04-01 08:00 | Wave 1 | I051 | Patient Education System | Tier 2 - Medium Governance | 6- Patient Engagement
Initiative 52: Secure patient engagement platform for conversing with the physicians | Amir Aziz | 0% | Gray | Empty | 2026-06-22 17:00 | Not Started | Not Started | 2025-10-13 08:00 | Wave 2 | I052 | Physician Patient Engagement Platform | Tier 3 - Low Governance | 6- Patient Engagement
Initiative 53: Deﬁne the data management oﬃce and strategy | Khawlah Alotaibi | 98% | Red | Three Quarter | 2025-02-27 17:00 | In Progress | Closure | 2024-12-01 08:00 | Wave 1 | I053 | Data Strategy & Governance | Tier 1 - High Governance | 7- Data Strategy & Enablement
Initiative 54: Implement Data platform & Data Lake | samaher abu samrah | 0% | Green | Empty | 2026-08-26 17:00 | In Progress | Assesment | 2025-03-16 08:00 | Wave 2 | I054 | Data Platform & Data Lake | Tier 2 - Medium Governance | 7- Data Strategy & Enablement
Initiative 55:Implement a Single data source of patient information: Master Data Management (MDM) | Khawlah Alotaibi | 24% | Gray | Empty | 2026-12-08 17:00 | In Progress | Procurement | 2025-06-01 08:00 | Wave 2 | I055 | Master Data Management (MDM) | Tier 2 - Medium Governance | 7- Data Strategy & Enablement
Initiative 56: Upgrade Centralized Reports and Dashboard systems | samaher abu samrah | 0% | Green | Empty | 2026-10-06 17:00 | Not Started | Not Started | 2025-03-30 08:00 | Wave 2 | I056 | Reports & Dashboard Upgrade | Tier 3 - Low Governance | 7- Data Strategy & Enablement
Initiative 57: Implement and enable a Digital Centre of excellence | samaher abu samrah | 0% | Gray | Empty | 2026-10-01 17:00 | Not Started | Not Started | 2026-04-01 08:00 | Wave 2 | I057 | Digital Center of Excellence | Tier 2 - Medium Governance | 8- Digital CoE to Drive Innovation
Initiative 58: Implement & Adopt emerging technologies | mahmoud alfaqih | 21% | Green | Empty | 2025-08-10 17:00 | In Progress | Planning | 2025-02-10 08:00 | Wave 2 | I058 | Emerging Tech Adoption (LCNC, Blockchain, AI) | Tier 2 - Medium Governance | 8- Digital CoE to Drive Innovation
Initiative 59: Define and execute the Sustainability strategy and roadmap | samaher abu samrah | 100% | Green | Full | 2026-01-15 17:00 | Complete | Completed | 2025-03-16 08:00 | Wave 2 | I059 | Sustainability Strategy | Tier 3 - Low Governance | 8- Digital CoE to Drive Innovation
Initiative 60: Introduce AI solutions for early diagnosis and detection of diseases | samaher abu samrah | 0% | Green | Empty | 2025-09-09 17:00 | Not Started | Not Started | 2025-03-09 08:00 | Wave 2 | I060 | AI for Early Disease Detection | Tier 1 - High Governance | 8- Digital CoE to Drive Innovation
Initiative 61: Introduce and operate Transformation Program Management office (TPMO) | samaher abu samrah | 42% | Green | Quarter | 2025-06-30 17:00 | In Progress | Implementation | 2024-11-01 08:00 | Wave 2 | I061 | TPMO Office Setup | Tier 2 - Medium Governance | 9- IT Operating Model
Initiative 62: Enterprise Architecture Office (EAO) | Ibaa Hanbali | 6% | Green | Empty | 2025-08-10 17:00 | In Progress | Initiation | 2025-02-10 08:00 | Wave 2 | I062 | Enterprise Architecture Office | Tier 2 - Medium Governance | 9- IT Operating Model
Initiative 63: Define Dallah new target IT operating model to accommodate CoE, TPMO and EA Office | mahmoud alfaqih | 0% | Gray | Empty | 2025-12-28 17:00 | Not Started | Not Started | 2025-08-03 08:00 | Wave 2 | I063 | IT Operating Model Upgrade | Tier 2 - Medium Governance | 9- IT Operating Model
Initiative 64: Revise and refresh cyber security strategy | Ibaa Hanbali | 0% | Gray | Empty | 2026-02-04 17:00 | Not Started | Not Started | 2025-08-03 08:00 | Wave 2 | I064 | Cybersecurity Strategy Update | Tier 2 - Medium Governance | 10- Cybersecurity
Initiative 65: Implement a IAM tool | Ibaa Hanbali | 5% | Green | Empty | 2025-09-02 17:00 | In Progress | Initiation | 2025-03-02 08:00 | Wave 1 | I065 | Identity & Access Management (IAM) | Tier 2 - Medium Governance | 10- Cybersecurity
Initiative 66: Implement a security operating center (SoC) | Ibaa Hanbali | 100% | Green | Full | 2026-04-15 17:00 | Complete | Closure | 2025-04-01 08:00 | Wave 1 | I066 | Security Operations Center (SOC) | Tier 1 - High Governance | 10- Cybersecurity
Initiative 67: Introduce AR/VR solutions for training | mahmoud alfaqih | 22% | Green | Empty | 2025-08-10 17:00 | In Progress | Planning | 2025-02-10 08:00 | Wave 2 | I067 | AR/VR for Training & Care | Tier 3 - Low Governance | 11- Digital Hospital of the future
Initiative 68: Introduce a Digital twin system | samaher abu samrah | 0% | Gray | Empty | 2026-12-02 17:00 | Not Started | Not Started | 2025-07-30 08:00 | Wave 3 | I068 | Digital Twin Implementation | Tier 2 - Medium Governance | 11- Digital Hospital of the future
Initiative 69: Introduce Robotic arm surgery | samaher abu samrah | 1% | Green | Empty | 2026-03-18 17:00 | Blocked | Assesment | 2025-03-16 08:00 | Wave 2 | I069 | Robotic Surgery | Tier 3 - Low Governance | 11- Digital Hospital of the future